## Slide 1: Essentials of Systems Analysis and Design Fifth Edition Joseph S. Valacich Joey F. George Jeffrey A. Hoffer
Chapter 4
Systems Planning and Selection
4.1

## Slide 2: Learning Objectives
Steps for identifying and selecting projects and initiating and planning projects
Content of and need for a project scope statement and baseline project plan
Methods for accessing project feasibility
Explain intangible and tangible costs and benefits
Explain recurring and one-time costs
Describe various methods of cost/benefit analysis
Describe a structured walkthrough
4.2

## Slide 3: Identifying and Selecting Projects
Sources of Projects
  Managers and business units
    To gain more information or provide new services
  Information systems managers
    To make a system more efficient, less costly, or want a new operating environment
  Formal planning groups
    To improve an existing system in order to help the organization meet its corporate objectives
    Often part of a larger plan
4.3

## Slide 4: Identifying and Selecting Projects
Three step process:
Identify potential projects
Classify and rank projects
Select projects
4.4

## Slide 5: Identifying and Selecting Projects
Projects are identified by a combination of top-down and bottom-up approaches
  Top-Down identification
    Senior management or steering committee
    Focus is on global needs of organization
  Bottom-up identification
    Business unit or IS group
    Don’t reflect overall goals of the organization
4.5

## Slide 6: Identifying and Selecting Projects
Classify and rank development projects
  See criteria Table 4-2, p.86
3. Select development projects
  Factors:
    Perceived needs of the organization
    Existing systems and ongoing projects
    Resource availability
    Evaluation criteria
    Current business conditions
    Perspectives of the decision makers
4.6

## Slide 7
4.7
Factors when selecting development projects

## Slide 8
4.8
Identifying and Selecting Projects - Deliverables and Outcomes
Incremental commitment
  Continuous reassessment of project after each phase

## Slide 9: Initiating and Planning System Development Projects
  Transform a vague systems request (SSR) into a tangible project description / plan.
Objectives
  Baseline Project Plan (BPP)
    Internal document; commitment from IS Execs
  Project Scope Statement (PSS)
    Prepared for external and internal stakeholders
    Provides a high-level overview of the project
    Gains commitment from user/customer Execs
4.9

## Slide 10: Baseline Project Plan Overview
Best estimate of the projects:
  Scope, alternatives
  Benefits
  Resource requirements
  Schedule
  Costs
  Risks
  Standards and procedures

## Slide 11: Assessing Project Feasibility
Six Categories
  Economic
  Operational
  Technical
  Schedule
  Legal and contractual
  Political
4.11

## Slide 12: Assessing Economic Feasibility
Cost–Benefit Analysis
Determine Benefits
  Tangible benefits
    Can be measured easily
      Examples
        Cost reduction and avoidance
        Error reduction
        Increased flexibility
        Increased speed of activity
        Increased management planning and control
4.12

## Slide 13: Assessing Economic Feasibility
  Intangible Benefits
    Cannot be measured easily
    Examples
      Increased organizational flexibility
      Increased employee morale
      Competitive necessity
      More timely information
      Promotion of organizational learning and understanding
4.13

## Slide 14
4.14
Assessing Economic Feasibility

## Slide 15: Assessing Economic Feasibility
Determine Costs
  Tangible Costs
    Can easily be measured in dollars
      Example: Hardware
  Intangible costs
    Cannot be easily measured in dollars
    Examples:
      Loss of customer goodwill
      Loss of employee morale
4.15

## Slide 16: Assessing Economic Feasibility
  One-Time Costs
    Associated with project start-up, initiation and development
    Includes
      System development
      New hardware and software purchases
      User training
      Site preparation
      Data or system conversion
4.16

## Slide 17: Assessing Economic Feasibility
  Recurring (Operational) Costs
    Associated with on-going use of the system
      New human resource costs
      Application software maintenance
      Incremental data storage expense
      Incremental communications
      New software and hardware releases
      Consumable supplies
  Time value of money (TVM)
    The process of comparing present cash outlays to future expected returns

## Slide 18
4.18
Try an example
spreadsheet

## Slide 19: Assessing Other Feasibility Concerns
Operational Feasibility
  Assessment of how a proposed system solves business problems or takes advantage of opportunities
Technical Feasibility
  Assessment of the development organization’s ability to construct a proposed system
4.19

## Slide 20: Assessing Other Feasibility Concerns
Schedule Feasibility
  Assessment of time-frame and project completion dates with respect to organization constraints for affecting change
Legal and Contractual Feasibility
  Assessment of legal and contractual ramifications of new system
4.20

## Slide 21: Assessing Other Feasibility Concerns (continued)
Political Feasibility
  Assessment of key stakeholders’ view in organization toward proposed system
4.21

## Slide 22: Risk Sources Ordered by Importance (Keil, Cule, Lyytinen, Schmidt)
1. Lack of top management commitment
2. Failure to gain user commitment
3. Misunderstanding of requirements
4. Inadequate user involvement
5. Failure to manage end-user expectations
6. Changing scope and/or objectives
7. Personnel lack required knowledge/skills
Notes: Sources of Risk
In identifying the sources of project risk , you can first include all of the sources of uncertainty mentioned earlier in this chapter, such as misapprehension of scope and changes in requirements. Some of these can’t properly be laid to rest until they are actually attempted, but crucial parts can be attacked early on. For example, with persistent communication, the core of the customer’s scope expectations can be discerned at this point.
The figure lists several sources of risk. One of these is tools such as design automation. Tool vendors can go out of business, discontinue support for the tool versions etc. (Indeed, this is one reason that computer-aided software engineering tools did not catch on in the 1980’s.) The mobility of software personnel is another source of risk.

## Slide 23: The Four Risk Activities
Identification (continual activity)
Analysis and Prioritization
Planning elimination or mitigation
Track and control
Adapted from Software Engineering: An Object-Oriented Perspective by Eric J. Braude (Wiley 2001), with permission.

## Slide 24: Risk Management In-Class Exercise
Each team member takes 5 minutes to identify risks to project success
  fill in probability, impact, retirememt method and costs on spreadsheet provided
One group member leads all to integrate and rationalize, and add any additional risks
Calculate priority (RBC, RAC) of risks
Rank priorities, determine most important
Suggest methods of retirement or mitigation and assign person responsible for follow-up

## Slide 25: Building the Baseline Project Plan
Objectives
  Assures that customer and development group have a complete understanding of the proposed system and requirements
  Provides sponsoring organization with a clear idea of scope, benefits and duration of project
4.25

## Slide 26: Building the Baseline Project Plan
Four Sections of a Baseline Project Plan:
  Introduction
  System description
  Feasibility assessment
  Management issues
4.26

## Slide 27
4.27

## Slide 28: Reviewing the Baseline Project Plan
Objectives
  Assure conformity to organizational standards
  All parties agree to continue with project
4.28

## Slide 29: Reviewing the Baseline Project Plan
Structured Walkthrough
  Peer group review
    Chair/Coordinator
    Presenter
    Reviewer (User)
    Secretary
    Standard Bearer
    Maintenance Oracle
  Activities
    Walkthrough review form
    Individuals polled
    Walkthrough action list
  Advantages
    Assures that review occurs during project
4.29

## Slide 30
4.30

## Slide 31
4.31